## FPSO
PROCUREMENT PLAN - KIZOMBA FPSO PHASE 1
Rev B
Date: 14/05/21
QTY | DESCRIPTION | OPTION | SUPPLIER | EST. COST | ORIGIN | EST. LEAD TIME | SHIPPING | CUSTOMS | NOTES | REF
CPI
201m | Top Chain Ø119mm R4 Studless, Length = 201m | Both | Vicinay Cadenas | 140726.3832 | Spain | 10 weeks | 4 weeks | 2 weeks | excess required for in line mooring tensioner methodology
|  |  | Vicinay Cadenas (FMAC) |  | China | 10 weeks | 5 weeks
|  |  | Intermoor | 124206.63 | USA | 12 weeks | 4 weeks
1500m | Sheathed Spiral Strand Wire MBL = 1165Te, Length = 1500m, Open Spelter Socket (both ends) | Both | Bridon |  | USA |  | 4 weeks | 2 weeks | Ø~108mm, due to diameter appears to be single source
142m | Bottom Chain Ø119mm R4 Studless, Length = 142m | Both | Vicinay Cadenas | 105545 | Spain | 10 weeks | 4 weeks | 2 weeks | excess required for chain tail on pile shackle
|  |  | Vicinay Cadenas (FMAC) |  | China | 10 weeks | 5 weeks
|  |  | Intermoor | 93372.12 | USA | 12 weeks | 4 weeks
2 | End joining shackle (Ø216mm chain to triplate) | Both | Vicinay Cadenas |  | Spain | 10 weeks | 4 weeks | 2 weeks
|  |  | Vicinay Cadenas (FMAC) |  | China | 10 weeks | 5 weeks
|  |  | Intermoor |  | USA | 12 weeks | 4 weeks
2 | Chain / Wire Triplate for Ø119mm R4 chain | Both | Vicinay Cadenas | 4513.19 | Spain | 10 weeks | 4 weeks | 2 weeks | 1x for ILMT
|  |  | Vicinay Cadenas (FMAC) |  | China | 10 weeks | 5 weeks
|  |  | Intermoor | 15347.49 | USA | 12 weeks | 4 weeks
2 | Connecting Pin for open spelter socket | Both | Bridon |  | USA |  | 4 weeks | 2 weeks
2 | End Joining Shackle for Ø119mm | Both | Vicinay Cadenas | 5054.77 | Spain | 10 weeks | 4 weeks | 2 weeks | 1x for ILMT
|  |  | Vicinay Cadenas (FMAC) |  | China | 10 weeks | 5 weeks
|  |  | Intermoor |  | USA | 12 weeks | 4 weeks
1 | Pile Joining Shackle Ø119mm | Both | Vicinay Cadenas | 5054.77 | Spain | 10 weeks | 4 weeks | 2 weeks | Variation from End shackle
|  |  | Vicinay Cadenas (FMAC) |  | China | 10 weeks | 5 weeks
|  |  | Intermoor |  | USA | 12 weeks | 4 weeks
1 | Suction Pile (Length = 26.985m; Ø6.32m) | Both | Welcon | 715532.98 | Denmark | 34 weeks | 4 weeks | 2 weeks
|  |  | Wilton Eng. Services | 1069575 | UK | 26 weeks | 4 weeks
1 | In line mooring tensioner end shackle (for Ø~108mm spiral strand) | ILMT | Vicinay Cadenas |  | Spain | 10 weeks | 4 weeks | 2 weeks
|  |  | Vicinay Cadenas (FMAC) |  | China | 10 weeks | 5 weeks
|  |  | Intermoor | 7016.0387 | USA | 12 weeks | 4 weeks
1 | Special Joining Shackle (Ø119mm) | Both | Vicinay Cadenas | 5054.77 | Spain | 10 weeks | 4 weeks | 2 weeks | Optional: for chain tail pile connection
|  |  | Vicinay Cadenas (FMAC) |  | China | 10 weeks | 5 weeks
|  |  | Intermoor |  | USA | 12 weeks | 4 weeks
OPERATIONAL EQUIPMENT
1 | Mobile Chain Tensioner | Like for Like | Royal IHC | - | Netherlands | - | 4 weeks | 2 weeks | Custom design likely for FPSO.
|  |  | PUSNES |  | UK | - | 4 weeks
1 | HPU for Mobile Chain Tensioner | Like for Like | MDL |  | UK | 4 - 6 weeks | 4 weeks | 2 weeks
|  |  | Hydraproducts |  | UK
1 | In Line Mooring Tensioner (for Ø119mm chain) | ILMT | Flintstone Technology |  | UK | 9 months | 4 weeks | 2 weeks | Vryhof / Royal IHC limited track record
|  |  | Vryhof | 113736.65 | Netherlands | 14 weeks
|  |  | Royal IHC |  | Netherlands
1 | Pull in Winch (circa 40Te) | Both | MDL |  | UK |  | 4 weeks | 2 weeks | Possibly Refurbished Main Winch - 4-6 weeks refurbishment
|  |  | Motive Offshore |  | UK | 14 - 16 weeks
1 | HPU for Pull in Winch | Both | MDL |  | UK | 4 - 6 weeks | 4 weeks | 2 weeks | Possibly Refurbished HPU - 4-6 weeks refurbishment
|  |  | Hydraproducts |  | UK
|  |  | Motive Offshore |  | UK | 14 - 16 weeks
1 | Pull in Winch grillage | Both | Dales |  | UK |  | 4 weeks | 2 weeks
|  |  | Motive Offshore |  | UK | 14 - 16 weeks
1 | Pull in Sheave | Both | Dales |  | UK |  | 4 weeks | 2 weeks
|  |  | Motive Offshore |  | UK | 14 - 16 weeks
1 | Pull in sheave foundation | Both | Dales |  | UK |  | 4 weeks | 2 weeks
|  |  | Motive Offshore |  | UK | 14 - 16 weeks
1 | Suction Pile Pump | Both | SPT | 350000 | UK |  | 4 weeks | 2 weeks
|  |  | AZ20 |  | UK
RIGGING
1 | Lifting Rigging (Mob to FPSO) | Both | [5 empty] | 2 weeks
1 | Winch Rigging | Both | [5 empty] | 2 weeks
1 | Mooring Line Recovery Rigging | Both | [5 empty] | 2 weeks
1 | Suction Pile Rigging | Both | [5 empty] | 2 weeks
1 | Grapnel | Both | [5 empty] | 2 weeks
1 | Chain tensioning rigging | Both | [5 empty] | 2 weeks
TOOLING
1 | Project Tooling | Both | [5 empty] | 2 weeks
1 | Survey Package (LBL Transponders) | Both | [5 empty] | 2 weeks
1 | Spooler | Both | [5 empty] | 2 weeks
1 | Oxycetalyne | Both | [5 empty] | 2 weeks
1 | ROV Work Basket | Both | [5 empty] | 2 weeks
1 | ROV Chain Cutter | Both | Cutting Underwater Tech. |  | UK | 4 weeks | 4 weeks | 2 weeks
1 |  | Both | [5 empty] | 2 weeks
VESSELS
1 | Maesk Achiever (AHT) | Both | MSS | - | - | - | - | - | Identified as optimal vessel
1 | Maersk AHT | Both | MSS | - | - | - | - | - | OPTIONAL - Dependent on Pile methodology
OTHER
Note: Document to be reviewed and updated throughout Project Life Cycle as procurement items become further defined

## CALM Buoy
PROCUREMENT PLAN - KIZOMBA CALM BUOY PHASE 1
Rev B
Date: 14/05/21
QTY | DESCRIPTION | OPTION | SUPPLIER | EST. COST | ORIGIN | EST. LEAD TIME | SHIPPING | CUSTOMS | NOTES | REF
CPI
1 | Mooring Connector | Both | SBM Offshore |  | - | - | - | 2 weeks | Casting; SBM Offshore designed (patented)
61m | Top Chain Ø152mm R3 Studless, Length = 61m | Both | Vicinay Cadenas | 69455.83 | Spain | 10 weeks | 4 weeks | 2 weeks | excess required for in line mooring tensioner methodology
|  |  | Vicinay Cadenas (FMAC) |  | China | 10 weeks | 5 weeks
|  |  | Intermoor | 53024.01 | USA | 12 weeks | 4 weeks
1896m | Sheathed Spiral Strand Wire MBL = 1165Te, Length = 1896m, Closed Spelter Socket (both ends) | Both | Bridon |  | USA |  |  | 2 weeks | Ø~83mm, due to diameter appears to be single source
150m | Bottom Chain Ø152mm R3 Studless, Length = 150m | Both | Vicinay Cadenas | 186995.59 | Spain | 10 weeks | 4 weeks | 2 weeks | excess required for chain tail on pile shackle
|  |  | Vicinay Cadenas (FMAC) |  | China | 10 weeks | 5 weeks
|  |  | Intermoor | 93372.12 | USA | 12 weeks | 4 weeks
2 | End joining shackle (Ø152mm to closed socket) | Both | Vicinay Cadenas | 8871.64 | Spain | 10 weeks | 4 weeks | 2 weeks | 1x for ILMT
|  |  | Vicinay Cadenas (FMAC) |  | China | 10 weeks | 5 weeks
|  |  | Intermoor |  | USA | 12 weeks | 4 weeks
1 | Pile Joining Shackle Ø152mm | Both | Vicinay Cadenas | 8871.64 | Spain | 10 weeks | 4 weeks | 2 weeks | Variation from End shackle
|  |  | Vicinay Cadenas (FMAC) |  | China | 10 weeks | 5 weeks
|  |  | Intermoor |  | USA | 12 weeks | 4 weeks
1 | Suction Pile (Length = 20.575m; Ø4.5m) | Both | Welcon | 715532.98 | Denmark | 34 weeks | 4 weeks | 2 weeks
|  |  | Wilton Eng. Services |  | UK | 26 weeks | 4 weeks
1 | In line mooring tensioner end shackle (for Ø~83mm spiral strand) | ILMT | Vicinay Cadenas |  | Spain | 10 weeks | 4 weeks | 2 weeks
|  |  | Vicinay Cadenas (FMAC) |  | China | 10 weeks | 5 weeks
|  |  | Intermoor |  | USA | 12 weeks | 4 weeks
1 | Special End Joining Shackle (Ø152mm; Mooring Connector) | Both | Vicinay Cadenas | 8871.64 | Spain | 10 weeks | 4 weeks | 2 weeks
|  |  | Vicinay Cadenas (FMAC) |  | China | 10 weeks | 5 weeks
|  |  | Intermoor |  | USA | 12 weeks | 4 weeks
1 | Special Joining Shackle (Ø152mm) | Both | Vicinay Cadenas | 8871.64 | Spain | 10 weeks | 4 weeks | 2 weeks | Optional: for chain tail pile connection
|  |  | Vicinay Cadenas (FMAC) |  | China | 10 weeks | 5 weeks
|  |  | Intermoor |  | USA | 12 weeks | 4 weeks
OPERATIONAL EQUIPMENT
1 | Mobile Chain Tensioner | Like for Like | Flint Tech | 600000 |  | 9 months
1 | HPU for Mobile Chain Tensioner | Like for Like | MDL? |  |  | 4 - 6 weeks
1 | In Line Mooring Tensioner (for Ø152mm chain) | ILMT | MacGregor / Flintstone Technology |  | UK |  | 4 weeks | 2 weeks | Vryhof / Royal IHC limited track record
|  |  | Vryhof | 204993.33 | Netherlands | 14 weeks
|  |  | Royal IHC |  | Netherlands
1 | Pull in Winch (circa 165Te) | Both | MDL |  | UK |  | 4 weeks | 2 weeks | Possibly Refurbished Main Winch - 4-6 weeks refurbishment
|  |  | Motive Offshore |  | UK | 14 - 16 weeks
1 | Pull in Winch (circa 30Te) | Both | MDL |  | UK |  | 4 weeks | 2 weeks | Possibly Refurbished Main Winch
|  |  | Motive offshore |  | UK | 14 - 16 weeks
1 | HPU for Pull in Winch | Both | MDL |  | UK | 4 - 6 weeks | 4 weeks | 2 weeks | Possibly Refurbished HPU - 4-6 weeks refurbishment
|  |  | Hydraproducts |  | UK
|  |  | Motive Offshore |  | UK | 14 - 16 weeks
1 | Pull in Winch grillage | Both | Dales |  | UK |  | 4 weeks | 2 weeks | Possibly refurbish original
|  |  | Motive Offshore |  | UK | 14 - 16 weeks
1 | Auxiliary Pull in Sheave | Both | Dales |  | UK |  | 4 weeks | 2 weeks | OPTIONAL
|  |  | Motive Offshore |  | UK | 14 - 16 weeks
1 | Auxiliary Pull in sheave foundation | Both | Dales |  | UK |  | 4 weeks | 2 weeks | OPTIONAL
|  |  | Motive Offshore |  | UK | 14 - 16 weeks
1 | Suction Pile Pump | Both | SPT SAPS | 400000 | UK |  | 4 weeks | 2 weeks |  | https://www.sptoffshore.com/equipment/suction-pumps/
|  |  | AZ20 |  | UK
RIGGING
1 | Lifting Rigging (Mob to FPSO) | Both | [5 empty] | 2 weeks
1 | Winch Rigging | Both | [5 empty] | 2 weeks
1 | Mooring Line Recovery Rigging | Both | [5 empty] | 2 weeks
1 | Suction Pile Rigging | Both | [5 empty] | 2 weeks
1 | Chain Recovery Rigging | Both | [5 empty] | 2 weeks
TOOLING
1 | Project Tooling | Both
1 | Survey Package (LBL) | Both
1 | Spooler | Both
1 | Oxy acetylene torch | Both
1 | Hydraulic torque wrench | Both
1 | ROV Wire Cutter | Both | Cutting Underwater Tech. |  | UK | 4 weeks | 4 weeks | 2 weeks
VESSELS
1 | Maesk Achiever (AHT) | Both | MSS | HOLD | - | - | - | - | Identified as optimal vessel
1 | Maersk AHT | Both | MSS | [5 empty] | OPTIONAL - Dependent on Pile methodology
OTHER
Note: Document to be reviewed and updated throughout Project Life Cycle as procurement items become further defined